## Project Tracker
Project Tracker
in hours
| Task | Category | Assigned To | ETA | Est. Work | Status
| overall Design | Design | Junfei(Tony) Gu |  | 4 | Done
| overall Design | Design | Shang Gao |  | 4 | Done
| overall Design | Design | Mather Warsame |  | 4 | Done
| overall Design | Design | Dan Zhang |  | 4 | Done
| overall Design | Design | Emma Sab |  | 4 | Done
| overall Design | Design | Yihong(Mike) Hu |  | 4 | Done
| implement the landscape in OBJ files | Landscape/Background | Junfei(Tony) Gu |  | 24 | Done
add texture to the landscape and background |  | Landscape/Background | Junfei(Tony) Gu |  | 24 | Done
add skybox in the background |  | Landscape/Background | Junfei(Tony) Gu |  | 18 | In-Progress
| put colors to the landscape and background | Landscape/Background | Junfei(Tony) Gu |  | 24 | Done
| build models | Models | Junfei(Tony) Gu |  | 18 | In-Progress
| Implement first person camera | Camera | Shang Gao |  | 12 | Done
| Implement third person camera | Camera | Shang Gao |  | 12 | Done
| build models | Models | Yihong(Mike) Hu |  | 8 | In-Progress
| Spline for the track | Spline | Dan Zhang |  | 48 | In-Progress
| Spline for the track | Spline | Mather Warsame |  | 48 | In-Progress
| Spline for the track | Spline | Shang Gao |  | 18 | In-Progress
| Define animations of the coaster | Animation | Emma Sab |  | 24 | Not-Started
| Define animations of the coaster | Animation | Yihong(Mike) Hu |  | 36 | Not-Started
| shading and lighting(if possible) | shading/lighting | Dan Zhang |  | 12 | In-Progress
| shading and lighting(if possible) | shading/lighting | Mather Warsame |  | 12 | In-Progress
| shading and lighting(if possible) | shading/lighting | Yihong(Mike) Hu |  | 12 | In-Progress
| shading and lighting(if possible) | shading/lighting | Junfei(Tony) Gu |  | 12 | In-Progress
| particle implementation (water) | Particles/Billboard | Shang Gao |  | 12 | Not-Started
| particle implementation (water) | Particles/Billboard | Emma Sab |  | 18 | Not-Started
| particle animation | Particles/Billboard | Shang Gao |  | 24 | Not-Started
| particle animation | Particles/Billboard | Emma Sab |  | 24 | Not-Started
SETUP

## Setup
Setup
| Category | Team members
| Design | Yihong(Mike) Hu
| Landscape/Background | Junfei(Tony) Gu
| Models | Shang Gao
| Camera | Dan Zhang
| Animation | Mather Warsame
| shading/lighting | Emma Sab
Particle/Billboard | Particles/Billboard
Spline
#NAME?
PROJECTS